## Sheet1
Risk Register 1
2021-01-15
Project Name: Behavioural Password Protection
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 | 1 | Unable to get the message across. Risk of miscommunication. | People | project manager to intervene and understand source of miscommunication | Alicia | Low | High - Dispute results in zero progress | Low
2 | 2 | Inability to achieve the programming requirement. | Technical | do proper research and seek advice | Terrence | Low | High - Unable to deliver project specifications | Low
3 | 5 | Unable to maximize individual's roles for the project. Unable to delegate roles to specific individual. | People | project manager to step in and know what specialties each individual has | Alicia | Low | Medium - Requires more communication and impede progress | Low
4 | 4 | Inability to achieve users' expectation | People | Gathering of users' feedback and suggestions to make corrections and improve our product. | Joel | Low | Medium - Readdressing the requirements will result in time taken. | Low
5 | 3 | Change of project scope. | People | Team members to discuss on the changes required for the prototype programme. | Joel | Medium | Medium - Need to add in and change some of the information and the programme. | Low
6 | 6 | Programmer's computer break down during development | Technical | There should also be an online copy of the program on the internet / Github where the developers can retrieve from. | Terrence /Alicia/Cui hui | Low | High - Unable to deliver project specifications | Low
7 | 7 | Programmer's computer break down during presentation | Technical | Make sure that there are at least 2 computers that has the software pre-loaded into their computers. There should also be an online copy on the internet / Github and a hard copy in a external hard disk. | Terrence /Alicia/Cui hui | Low | High - Unable to present our code, hence signication deduction of marks | Low

## Sheet2
Probability Matrix
2021-01-15
high
5
medium
|  |  |  | 3, 4 |  | 1, 2, 6, 7
low
|  |  | low |  | medium |  | high
Impact
Probability